## Cover Page
Event Management System

## Doc Info
Test Script Information
FDD Reference No |  | Event Management System
Other related documents
Functional Domain
Document Version Control
Version | Date | Author | Reason for update
01 | 2014-11-10 | Shrijan Karmacharya | Draft
02 | 2014-12-10 | Purnesh Dixit | Updation

## Instructions
Instructions
Test Scenarios worksheet is to list the test scenarios (if applicable), purpose of each test scenario, expected results. State the actual result for each executed test cycle. Test Scenario - worksheet is to contain detailed description on how to execute testing for respective test scenario. TS represents test screnario # is number sign Example TS2 - means test scenario 2. The worksheet is to include the test result for each steps. Testing Defect Log worksheet is applied for the defects encountered during the testing and it's respective result after being resolved or reworked by the development team.

## Test Scenarios
Test Scenarios Result Summary |  | Iteration 1 |  |  |  |  | Iteration 2 |  |  |  |  | Iteration 3
|  |  | Planned |  | Actual |  |  | Planned |  | Actual |  |  | Planned |  | Actual
TS# | Description | Result | Start | End | Start | End | Result | Start | End | Start | End | Result | Start | End | Start | End
TS1 | Check if employee creation and update are possible | Pass | 2014-09-22 | 24 Oct,2014 | 24 Oct,2014 | 24 Oct,2014 | Pass | 2014-12-10 | 2014-12-10
TS2 | Check if creation and update for employee and family details are possible | Pass | 2014-09-22 | 24 Oct,2014 | 24 Oct,2014 | 24 Oct,2014
Note on B4: Jyoti kalra: Test scenario number
Note on C4: Jyoti kalra: Test Scenario Description
Note on D4: Jyoti Kalra: Not started Pass Fail Cancelled On hold Deffered
Note on E4: Jyoti Kalra: 16 april, 2014
Note on F4: Jyoti Kalra: 8 April, 2014
Note on H4: Jyoti Kalra: 18 April,2014
Note on I4: Vikas Garg: Not started Pass Fail Cancelled On hold Deffered
Note on J4: Jyoti Kalra: 23 April,2014
Note on K4: Jyoti Kalra: 23 April,2014
Note on L4: Jyoti Kalra: 23 April,2014
Note on M4: Jyoti Kalra: 23 April,2014
Note on N4: Vikas Garg: Not started Pass Fail Cancelled On hold Deffered
Note on O4: Jyoti Kalra: 23 April,2014
Note on P4: Jyoti Kalra: 23 April,2014
Note on Q4: Jyoti Kalra: 23 April,2014
Note on R4: Jyoti Kalra: 23 April,2014

## Test Cases
| Test Type | Functional Test | Prerequisites:
| Build Number: |  | Tester Must have administrator privilages
| Tester | Shrijan Karmacharya, Purnesh Dixit
| Date | 2014-11-10
|  |  | Iteration 1 |  |  | Iteration 2 |  |  |  | Iteration 3
TC# | Description | Execution steps | Date | Result | Comments | Date2 | Result3 | Comments4 | Notes | Date2 | Result3 | Comments4 | Notes
TS1.01 | To check if it is possible to create new employees | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Employee Master. 3. Click the Worker -> New -> Hire new worker button. | 2014-11-10 | Pass
TS1.02 | To check if created employee can be deleted | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Employee Master. 3. Click the Worker -> Maintain -> Delete button. | 2014-11-10 | Pass | Cannot delete employees with position selected
TS1.03 | To check if there exists a reference to all created employees in FthEmployeeMaster table | 1. Go to Project -> FthEventManagement -> Data Dictionary -> Tables -> FthEmployeeMaster 2. Check the HCMWorker field for RecId of the newly created employee | 2014-11-10 | Pass
TS1.04 | To check if deletion of employee deletes reference from FthEmployeeMaster table | 1. Go to Project -> FthEventManagement -> Data Dictionary -> Tables -> FthEmployeeMaster 2. Check the HCMWorker field for RecId of the deleted employee still exists | 2014-11-10 | Pass
TS1.05 | To check if multiple employees with the same name can be created | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Employee Master. 3. Click the Worker -> New -> Hire new worker button. | 2014-11-10 | Pass | Asks if you want to use the previously created employee with the same name
TS1.06 | To check if past workers, retired workers etc. are not included for our module | 1. Go to the HR module 2. Click Area Page node: HR -> Common -> Past workers 3. Note any one of the Personnel number 4. Click Area Page node: Event Management -> Common -> Employee 5. Search that Personnel number 6. Also go to Employee Invitation at Area Page node: Event Management -> Employee Invitation and check if that personnel number is there under Employee tab in Employee List | 2014-11-10 | Pass
TS2.01 | To check if it is possible to add/modify surround/preference details for employee | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Employee Master. 3. Click the Worker -> Related Information-> Surround Details. | 2014-11-10 | Pass
TS2.02 | To check if it is possible to add/modify family details for employees | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Employee Master. 3. Click the Worker -> Related Information-> Family Details. | 2014-11-10 | Pass
TS2.03 | To delete an employee from HCMWorker and check if all related data is deleted from FthEmployeeSurroundDetails and FthEmployeeFamilySurroundDetails | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Employee Master. 3. Click the Worker -> Maintain -> Delete button. | 2014-11-10 | Pass
TS2.04 | Factboxes should reflect changes made in family details and employee surround details | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Employee Master. 3. Click the Worker -> Related Information-> Family Details. 4. Click the Worker -> Related Information-> Surround Details. | 2014-11-10 | Pass
Note on A8: Jyoti Kalra: Test Case No.
Note on B8: Jyoti Kalra: Test Case Description
Note on C8: Jyoti Kalra: Test Case Execution steps
Note on D8: Jyoti Kalra: Test Case Date
Note on E8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred
Note on F8: Jyoti Kalra: Comments
Note on G8: Jyoti Kalra: 9 April,2014
Note on H8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred
Note on K8: Jyoti Kalra: 9 April,2014
Note on L8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred

## Test Defect Log
Test Environment: Dev Machine | Note
Environment:
Company:
Dynamics AX version:
Rich Client / Web Client:
TC# | Defect Type | Defect Description | Steps to reproduce | Other reference number | Result | Notes
Note on A7: Jyoti Kalra: Test Case No
Note on B7: Jyoti Kalra: Logic Error Design Error Computational Error Data error
Note on D7: Jyoti Kalra: Steps To Reproduce
Note on F7: Jyoti Kalra: Pass Fail Deferred On Hold Cancelled
Note on G7: Jyoti Kalra: Notes

## Legend
Defect Type
Functionality Deviation
Functionality Loss
Missing Link
Design Issues
Unable to reproduce
Change Request
As Designed
Staandard AX Defect
Duplicate
Technical Feasbility Issue
Functional Domain
Finance
Projects
Procurement
Time & Expenses
Human Resources
Media
Rich Client / Web Client
Rich Client
Web Client
Test case status
Pass
Fail
Deffered
Cancelled
On hold