## Cover Page
Event Management System

## Doc Info
Test Script Information
FDD Reference No |  | Event Management System
Other related documents
Functional Domain
Document Version Control
Version | Date | Author | Reason for update
01 | 2014-11-11 | Shrijan Karmacharya | Draft
02 | 2014-12-10 | Purnesh Dixit | Updation

## Instructions
Instructions
Test Scenarios worksheet is to list the test scenarios (if applicable), purpose of each test scenario, expected results. State the actual result for each executed test cycle. Test Scenario - worksheet is to contain detailed description on how to execute testing for respective test scenario. TS represents test screnario # is number sign Example TS2 - means test scenario 2. The worksheet is to include the test result for each steps. Testing Defect Log worksheet is applied for the defects encountered during the testing and it's respective result after being resolved or reworked by the development team.

## Test Scenarios
Test Scenarios Result Summary |  | Iteration 1 |  |  |  |  | Iteration 2 |  |  |  |  | Iteration 3
|  |  | Planned |  | Actual |  |  | Planned |  | Actual |  |  | Planned |  | Actual
TS# | Description | Result | Start | End | Start | End | Result | Start | End | Start | End | Result | Start | End | Start | End
TS1 | Setup parameters and validations | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
TS2 | Creation and setup of event type group | On hold | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
TS3 | Creation and setup of event types | On hold | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
TS4 | Creation and setup of Food Preferences | Pass | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
TS5 | Creation and setup of Pickup drop location | Pass | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
TS6 | Creation and setup of allergies | Pass | 10 Nov, 2014 | 10 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014
TS7 | Creation,update and setup of events | On hold | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
TS8 | Setup of Food preferences for event | Pass | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
TS9 | Setup of Pickupdrop location for event | Pass | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | 11 Nov, 2014 | Pass | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014 | 10 Dec, 2014
Note on B4: Jyoti kalra: Test scenario number
Note on C4: Jyoti kalra: Test Scenario Description
Note on D4: Jyoti Kalra: Not started Pass Fail Cancelled On hold Deffered
Note on E4: Jyoti Kalra: 16 april, 2014
Note on F4: Jyoti Kalra: 8 April, 2014
Note on H4: Jyoti Kalra: 18 April,2014
Note on I4: Vikas Garg: Not started Pass Fail Cancelled On hold Deffered
Note on J4: Jyoti Kalra: 23 April,2014
Note on K4: Jyoti Kalra: 23 April,2014
Note on L4: Jyoti Kalra: 23 April,2014
Note on M4: Jyoti Kalra: 23 April,2014
Note on N4: Vikas Garg: Not started Pass Fail Cancelled On hold Deffered
Note on O4: Jyoti Kalra: 23 April,2014
Note on P4: Jyoti Kalra: 23 April,2014
Note on Q4: Jyoti Kalra: 23 April,2014
Note on R4: Jyoti Kalra: 23 April,2014

## Test Cases
| Test Type | Functional Test | Prerequisites:
| Build Number: |  | Tester Must have administrator privilages
| Tester | Shrijan Karmacharya, Purnesh Dixit
| Date | 24 Oct, 2014, 10 Dec, 2014
|  |  | Iteration 1 |  |  | Iteration 2 |  |  |  | Iteration 3
TC# | Description | Execution steps | Date | Result | Comments | Date2 | Result2 | Comments2 | Notes | Date2 | Result3 | CommenTS3 | Notes
TS1.01 | Displays all fields related to event for wrokflow resubmission on updation | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event management setup parameters | 2014-12-10 | Pass
TS1.02 | Excludes the primary key, system, foreign key etc. fields | 1. Go to Development environment(Ctrl+D) 2. Open FthEventManagement project and go to DataDictionary node. 3. See the fields of all the event tables and related tables. 4. Match the fields with the one displayed in the setup parameeter form at Event Management -> Setup -> Event management setup parameters | 2014-12-10 | Pass | Fields mentioned in the description shouldn't be present in the form
TS1.03 | Can select none or many fields displayed and kept as selected till we make any changes | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event management setup parameters 3. Select any no. of fields. Close the form. 4. Open the form again and check if the same fields are selected | 2014-12-10 | Pass
TS2.01 | To check if it is able to create new event type group and update it | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type Group 3. Click the New button/double click record to edit. | 2014-11-11 | Pass
TS2.02 | To check if it is possible to delete event type group | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type Group 3. Click the Delete button. | 2014-11-11 | Pass
TS2.03 | To check if deletion of event type group deletes corresponding event types | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type 3. Check if the related event group is deleted. | 2014-11-11 | Pass
TS2.04 | To check if reference to Event group type is created in FthEventTypeMaster Table | 1. Go to Project -> FthEventManagement -> Data Dictionary -> Tables -> FthEventTypeMaster 2. Check the EventTypeGroup field for RecId of the deleted employee still exists | 2014-11-11 | Pass
TS2.05 | To check if deletion of event type group deletes reference in Event Table | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Check Event type name field. | 2014-11-11 | Fail | Event type gets deleted but the Event Type field in FthEventDetails still has reference to it
TS2.06 | To check if setup field parameter form opens from Event type groups form | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type Group 3. Click on setup field parameters. | 2014-12-10 | Pass
TS2.07 | To check if Use default is checked on setup parameter form it should have same field checked as initial setup and grid should be disabled | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type Group 3. Click on setup field parameters. 4. Match the checked fields with inital setup | 2014-12-10 | Pass | If use default is checked, initial setup and the selected record should have same field(s) checked
TS2.08 | To check if Use default is not checked on setup parameter form it should allow to select any no. of fields and grid should be enabled. | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type Group 3. Click on setup field parameters. 4. Select any no. of fields. Close the form. 5. Open the form again and check if the same fields are selected | 2014-12-10 | Pass | Same fields as selected before should be checked for the selected record
TS3.01 | To check if it is able to create new event type and update it | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type Group 3. Click the New button/double click record to edit. | 2014-11-11 | Pass
TS3.02 | To check if it is possible to delete event type | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Type Group 3. Click the Delete button. | 2014-11-11 | Pass
TS3.03 | To check if deletion of event type deletes reference in Event Table | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Check Event type name field. | 2014-11-11 | Fail | FthEventDetails table still has reference to deleted Event type
TS3.04 | To check if setup field parameter form opens from Event types form | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Types 3. Click on setup field parameters. | 2014-12-10 | Pass
TS3.05 | To check if Use default is checked on setup parameter form it should have same field checked as the selected Event type group name setup and grid should be disabled | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Types 3. Click on setup field parameters. 4. Match the checked fields with the selected Event type group name from Event type groups setup field parameters. 5. Go to the Event Management module. 6. Click Setup node: Event Management -> Setup -> Event Type Group 7. Select that Event type group and Click on setup field parameters. 8. Match the checked fields | 2014-12-10 | Pass | If use default is checked, selected Event types setup and the selected Event type group should have same field(s) checked
TS3.06 | To check if Use default is not checked on setup parameter form it should allow to select any no. of fields and grid should be enabled. | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Event Types 3. Click on setup field parameters. 4. Select any no. of fields. Close the form. 5. Open the form again and check if the same fields are selected | 2014-12-10 | Pass | Same fields as selected before should be checked for the selected record
TS4.01 | To create and edit food preference | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Food Preference. 3. Click the New button. | 2014-11-11 | Pass
TS4.02 | To delete food preference | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Food Preference. 3. Click the Delete button. | 2014-11-11 | Pass
TS4.03 | To check if deleting food preferences removes all its references | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Check event factbox for deleted food preferences. | 2014-11-11 | Pass
TS5.01 | To create and edit pickup drop location | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Pickupdrop Location. 3. Click the New button. | 2014-11-11 | Pass
TS5.02 | To delete pickup drop location | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Pickupdrop Location. 3. Click the Delete button. | 2014-11-11 | Pass
TS5.03 | To check if deleting pickupdrop location removes all its references | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Check event factbox for deleted pickupdrop location. | 2014-11-11 | Pass
TS5.04 | To check if corresponding address of the selected location is displayed in address field | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Pickupdrop Location. 3. Select the different locations and seet the corresponding address | 2014-12-10 | Pass
TS5.05 | To check if new address can be created with its location appearing for the new Pick up drop location | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Pickupdrop Location. 3. Click on new address | 2014-12-10 | Pass
TS6.01 | To check if it is possible to create and update new allergies | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Allergies. 3. Click the New button. | 2014-11-11 | Pass
TS6.02 | To check if it is possible to delete allergies | 1. Go to the Event Management module. 2. Click Setup node: Event Management -> Setup -> Allergies. 3. Click the Delete button. | 2014-11-11 | Pass
TS7.01 | To check if it is possible to create an event | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> New -> Event button. | 2014-11-11 | Pass
TS7.02 | To check if it is possible to update the event | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> Maintain -> Edit button. | 2014-11-11 | Pass |  | 2014-12-10 | Pass | If event is not in draft mode and the updating field has been set up as required workflow resubmission for that particular event or at its upper levels, it will pop up a dialog with a warning and on selection of yes only updation will be allowed and event will go in draft state, resulting in cancelation of approvals and invitations
TS7.03 | To check if it is possible to delete the event | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> Maintain -> Delete button. | 2014-11-11 | Pass |  | 2014-12-10 | Pass | The event can be deleted only if its in draft, canceled or completed state
TS7.04 | To check for validation on event start date, event end date and respond by field | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> New -> Event button. 3. Check all dates entering 10th November, put end date before start date and response deadline after start date. | 2014-11-11 | Fail | All validations work fine on their own, however on editing the event, putting the start date after end date is allowed. | 2014-12-10 | Pass | The previous issue is resolved and on changing start date, end date and respond by is modified accordingly
TS7.05 | To check if setup field parameter form opens from Event form | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click on setup field parameters. | 2014-12-10 | Pass
TS7.06 | To check if Use default is checked on setup parameter form it should have same field checked as the selected Event type name setup and grid should be disabled | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click on setup field parameters. 4. Match the checked fields with the selected Event type name from Event typs setup field parameters. 5. Go to the Event Management module. 6. Click Setup node: Event Management -> Setup -> Event Types 7. Select that Event type and Click on setup field parameters. 8. Match the checked fields | 2014-12-10 | Pass | If use default is checked, selected Event setup and the selected Event type setup should have same field(s) checked
TS7.07 | To check if Use default is not checked on setup parameter form it should allow to select any no. of fields and grid should be enabled. | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click on setup field parameters. 4. Select any no. of fields. Close the form. 5. Open the form again and check if the same fields are selected | 2014-12-10 | Pass | Same fields as selected before should be checked for the selected record
TS8.01 | To add food preferences to event | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> New -> Event button. 4. Create a new event. 5. Click the Event Preferences -> Food Preferences fast tab. | 2014-11-11 | Pass |  | 2014-12-10 | Pass | If event is not in draft mode and the updating field has been set up as required workflow resubmission for that particular event or at its upper levels, it will pop up a dialog with a warning and on selection of yes only updation will be allowed and event will go in draft state, resulting in cancelation of approvals and invitations
TS8.02 | To remove food preferences of an event | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> Edit-> Event button. 5. Click the Event Preferences -> Food Preferences fast tab. | 2014-12-10 | Pass | Cannot remove selected food preferences if the event is published
TS9.01 | To add pickupdrop location to event | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> New -> Event button. 4. Create a new event. 5. Click the Event Preferences -> Pickupdrop Location fast tab. | 2014-11-11 | Pass |  | 2014-12-10 | Pass | If event is not in draft mode and the updating field has been set up as required workflow resubmission for that particular event or at its upper levels, it will pop up a dialog with a warning and on selection of yes only updation will be allowed and event will go in draft state, resulting in cancelation of approvals and invitations
TS9.02 | To remove pick up drop locations of an event | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Click the Event -> Edit -> Event button. 5. Click the Event Preferences -> Pickup drop location fast tab. | 2014-12-10 | Pass | Cannot remove selected pickup drop location if the event is published
Note on A8: Jyoti Kalra: Test Case No.
Note on B8: Jyoti Kalra: Test Case Description
Note on C8: Jyoti Kalra: Test Case Execution steps
Note on D8: Jyoti Kalra: Test Case Date
Note on E8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred
Note on F8: Jyoti Kalra: Comments
Note on G8: Jyoti Kalra: 9 April,2014
Note on H8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred
Note on K8: Jyoti Kalra: 9 April,2014
Note on L8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred

## Test Defect Log
Test Environment: | Note
Environment:
Company:
Dynamics AX version: 2012 R3
Rich Client / Web Client: Rich Client
TC# | Defect Type | Defect Description | Steps to reproduce | Other reference number | Result | Notes
TS1.05 | Design Error | Deletion of record does not remove all references to that record
TS2.03 | Design Error | Deletion of record does not remove all references to that record
TS6.04 | Design Error | Upon editing allows start date to be after end date
Note on A7: Jyoti Kalra: Test Case No
Note on B7: Jyoti Kalra: Logic Error Design Error Computational Error Data error
Note on D7: Jyoti Kalra: Steps To Reproduce
Note on F7: Jyoti Kalra: Pass Fail Deferred On Hold Cancelled
Note on G7: Jyoti Kalra: Notes

## Legend
Defect Type
Functionality Deviation
Functionality Loss
Missing Link
Design Issues
Unable to reproduce
Change Request
As Designed
Staandard AX Defect
Duplicate
Technical Feasbility Issue
Functional Domain
Finance
Projects
Procurement
Time & Expenses
Human Resources
Media
Rich Client / Web Client
Rich Client
Web Client
Test case status
Pass
Fail
Deffered
Cancelled
On hold