## Cover Page
Event Management System

## Doc Info
Test Script Information
FDD Reference No |  | Event Management System
Other related documents
Functional Domain
Document Version Control
Version | Date | Author | Reason for update
01 | 2014-11-11 | Purnesh Dixit | Draft

## Instructions
Instructions
Test Scenarios worksheet is to list the test scenarios (if applicable), purpose of each test scenario, expected results. State the actual result for each executed test cycle. Test Scenario - worksheet is to contain detailed description on how to execute testing for respective test scenario. TS represents test screnario # is number sign Example TS2 - means test scenario 2. The worksheet is to include the test result for each steps. Testing Defect Log worksheet is applied for the defects encountered during the testing and it's respective result after being resolved or reworked by the development team.

## Test Scenarios
Test Scenarios Result Summary |  | Iteration 1 |  |  |  |  | Iteration 2 |  |  |  |  | Iteration 3
|  |  | Planned |  | Actual |  |  | Planned |  | Actual |  |  | Planned |  | Actual
TS# | Description | Result | Start | End | Start | End | Result | Start | End | Start | End | Result | Start | End | Start | End
TS1 | Prepare outlook invitations | Pass | 2014-12-10 | 2014-12-10 | 2014-12-10 | 2014-12-10
TS2 | Send outlook invitations & acknowledgement mails
TS3 | Fetch outlook response and updating the history
Note on B4: Jyoti kalra: Test scenario number
Note on C4: Jyoti kalra: Test Scenario Description
Note on D4: Jyoti Kalra: Not started Pass Fail Cancelled On hold Deffered
Note on E4: Jyoti Kalra: 16 april, 2014
Note on F4: Jyoti Kalra: 8 April, 2014
Note on H4: Jyoti Kalra: 18 April,2014
Note on I4: Vikas Garg: Not started Pass Fail Cancelled On hold Deffered
Note on J4: Jyoti Kalra: 23 April,2014
Note on K4: Jyoti Kalra: 23 April,2014
Note on L4: Jyoti Kalra: 23 April,2014
Note on M4: Jyoti Kalra: 23 April,2014
Note on N4: Vikas Garg: Not started Pass Fail Cancelled On hold Deffered
Note on O4: Jyoti Kalra: 23 April,2014
Note on P4: Jyoti Kalra: 23 April,2014
Note on Q4: Jyoti Kalra: 23 April,2014
Note on R4: Jyoti Kalra: 23 April,2014

## Test Cases
| Test Type | Functional Test | Prerequisites:
| Build Number: |  | Tester Must have administrator privilages. The event should be in published state. Exchange web service username and password should be entered at email parameters form. Batch "Outlook invitaions processing" should be running.
| Tester | Purnesh Dixit
| Date | 10 Dec, 2014
|  |  | Iteration 1 |  |  | Iteration 2 |  |  |  | Iteration 3
TC# | Description | Execution steps | Date | Result | Comments | Date2 | Result2 | Comments2 | Notes | Date2 | Result3 | CommenTS3 | Notes
TS1.01 | To check if invitations can be submitted | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Select an event which is in publish state from the list. 4. Click on Send outlook invites | 2014-12-10 | Pass | It willl submit the invites for invited employees only
TS1.02 | To check the history of outlook invitations to be sent | 1. Go to System Administration module 2. Click on Area Page Node: System Administration -> Periodic -> Email processing -> Email sending status 3. Check show outlook invites | 2014-12-10 | Pass | The status of the email corresponding to the event for which the invitation is sent will be Waiting
TS2.01 | To check if the outlook invitations are getting sent | 1. Go to System Administration module 2. Click on Area Page Node: System Administration -> Periodic -> Email processing -> Email sending status 3. Check show outlook invites | 2014-12-10 | Pass | The time taken for completion of sending invitation is approx. 20 mins to 30 mins. The status of the email corresponding to the event for which the invitation is sent will be Sent.
TS2.02 | To check if the acknowledgement mail is sent to people who have accepted the invitation | 1. Go to System Administration module 2. Click on Area Page Node: System Administration -> Periodic -> Email processing -> Email sending status 3. Check Also show sent emails | 2014-12-10 | Pass | The time taken for completion of sending acknowledgement mail depends on the invitee acceptance. The status of the email corresponding to the event for which the invitation is sent will be Sent.
TS3.01 | Check the updation done based on outlook response of invitee | 1. Go to the Event Management module. 2. Click Area Page node: Event Management -> Common -> Event Details. 3. Select the event for which the history is to be checked. 4. Click on attendees information | 2014-12-10 | Pass | The time taken for completion of sending acknowledgement mail depends on the invitee acceptance/rejection. The same status(Accept/Decline) should appear for the invitee.
Note on A8: Jyoti Kalra: Test Case No.
Note on B8: Jyoti Kalra: Test Case Description
Note on C8: Jyoti Kalra: Test Case Execution steps
Note on D8: Jyoti Kalra: Test Case Date
Note on E8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred
Note on F8: Jyoti Kalra: Comments
Note on G8: Jyoti Kalra: 9 April,2014
Note on H8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred
Note on K8: Jyoti Kalra: 9 April,2014
Note on L8: Jyoti Kalra: Pass Fail On Hold Cancelled Deferred

## Test Defect Log
Test Environment: | Note
Environment:
Company:
Dynamics AX version: 2012 R3
Rich Client / Web Client: Rich Client
TC# | Defect Type | Defect Description | Steps to reproduce | Other reference number | Result | Notes
TS1.05 | Design Error | Deletion of record does not remove all references to that record
TS2.03 | Design Error | Deletion of record does not remove all references to that record
TS6.04 | Design Error | Upon editing allows start date to be after end date
Note on A7: Jyoti Kalra: Test Case No
Note on B7: Jyoti Kalra: Logic Error Design Error Computational Error Data error
Note on D7: Jyoti Kalra: Steps To Reproduce
Note on F7: Jyoti Kalra: Pass Fail Deferred On Hold Cancelled
Note on G7: Jyoti Kalra: Notes

## Legend
Defect Type
Functionality Deviation
Functionality Loss
Missing Link
Design Issues
Unable to reproduce
Change Request
As Designed
Staandard AX Defect
Duplicate
Technical Feasbility Issue
Functional Domain
Finance
Projects
Procurement
Time & Expenses
Human Resources
Media
Rich Client / Web Client
Rich Client
Web Client
Test case status
Pass
Fail
Deffered
Cancelled
On hold